## Project with Gantt Timeline
At Risk | Community Led Cycle or Walking Trail | Status | Start Date | End Date | Assigned To | % Complete | Notes
Red, amber or green | (Amend as appropriate for your project) | (Complete/in progress or not started) |  |  |  |  | Manage your expectation
Do not underestimate the time the Trail will take to initiate, plan, design and construct. This project could take years. Be aware and be committed! Kia Ora...
| Section 1 - Project Initiation Phase |  |  |  |  | 36%
| Sub-task 1 - Project Team created with key roles defined |  |  |  |  | 50%
| Sub-task 2 - Project Scope defined |  |  |  |  | 50%
| Sub-task 3 - Initial engagement with key stakeholders i.e. Council, Iwi/hapu, DOC Landowners etc |  |  |  |  | 0%
| Sub task 4 - Council formal support | [5 empty] | Ensure sufficient time to obtain consents and permits e.g resource, wildlife and arch authorities
Section 2 - Planning & Investigation (Scoping Design) Phase
Sub-task 1 - Fit for purpose review
Sub-task 2 - Safety reviews (SSAF or RSA)
Sub-task 3
Section 3 - Community Engagement Phase
Sub-task 1 - create a Community & Engagement Strategy document
Sub-task 2 - get signed off by Governance Group
Sub-task 3 -
Sub-task 1
Sub-task 2
Section 4 - Detailed Design & Property Phase
Sub-task 1 - Safety reviews (RSA)
Sub-task 2
Section 5 - Construction Phase
Sub-task 1 - H&S
Sub-task 2 - Procurement
Sub-task 3 - Sod turning event
Sub-task 4 - Build
Sub-task 5 - Post construction
Sub-task 1 - RSA, maintenance accepting
Sub-task 6 - Planting
Sub-task 7 - Opening event
Section 6 - Close Out/Stewardship/Vesting phase
Sub-task 1 - RAMM, as built drawings
Sub-task 2 - which department owns assets and which has custodianship

## Comments
Row 3 | Attach documents relevant to the task Or link to web documents | Linda Diep | 03/08/18 6:00 PM